## Sheet1
,
Sprint Backlog
| User Stories | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Members | Acceptance Criteria
| As a user I should be able to create a new account on android app. | Learn Firebase to store user data | 14 | 21 | 13 | 8 | 5 | 3 | Sunday (HOLIDAY) | 2 | 1 | 0 | 0 | 0 | 0 | Sunday (HOLIDAY) | Iqra, Saif ,Maham | User should be able to signup and his/her data should be stored securely And the UI should be effective and efficent.
|  | Design Registration from UI | 12 | 8 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Kashan
|  | Code to create a unique id for user | 25 | 27 | 19 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | Iqra, Saif ,Maham
|  | Design database | 18 | 8 | 5 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Iqra, Saif ,Maham
|  | Connect user data to server | 11 | 8 | 5 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Saif
| As a user I should be able to add my family members number on my app. | Provide number adding option | 12 | 21 | 13 | 8 | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 |  | Iqra, Saif ,Maham | user should be able to feed their specific number and set them on as their criteria
|  | Design UI add number | 15 | 25 | 18 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | kashan
|  | Connect server to app so that user can ale to send location via push notification | 13 | 13 | 8 | 5 | 5 | 3 |  | 2 | 1 | 1 | 0 | 0 | 0 |  | Iqra, Saif ,Maham
| As an admin I can send the current location of user to specified number via push notification. | Provide current location via google API's to all users. | 18 | 21 | 13 | 8 | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 |  | Iqra, Saif ,Maham | After user added all details, appshould be able to sendhis current location via push notifiaction.
|  | Design UI to detect no go area | 8 | 8 | 8 | 5 | 5 | 3 |  | 1 | 0 | 0 | 0 | 0 | 0 |  | Iqra, Saif ,Maham
|  | Design firebase push notification | 25 | 25 | 18 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | Iqra
|  | Connect server to app, so server can send current location. | 13 | 13 | 8 | 5 | 5 | 3 |  | 2 | 1 | 1 | 0 | 0 | 0 |  | Saif
Group Member 1 | Ayesha Zulfiqar | Scrum Master
Seat No. | (EP-1850023)
Group Member 2 | Iqra Shafqat | Developer 1
Seat No. | (EP-1850041)
Group Member 3 | Syed Saif Ali Abidi | Developer 2
Seat No. | (EP-1850125)
Group Member 4 | Kashan Khan | UI/UX Designer
Seat No. | (EP-1850074)
Group Member 5 | Mehtab Fatima | PRODUCT OWNER
Seat No. | (EP-1850052)